## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US01 | As a developer, I want raw bug reports to be preprocessed so that important diagnostic information is extracted in a structured form. | Must Have | None | Vaishali | Completed
1 | 1 | US02 | As a developer, I want exception type, priority, affected file, line number, keywords, and stack trace to be extracted from a bug report. | Must Have | US01 | Vaishali | Completed
1 | 1 | US03 | As a developer, I want processed bug information to be saved as structured JSON for downstream analysis. | Must Have | US01, US02 | Vaishali | Completed
2 | 2 | US04 | As a user, I want to upload PDF/TXT documents and extract their text for preprocessing and analysis. | Should Have | None | Vaishali | Completed
2 | 2 | US05 | As a developer, I want basic NLP preprocessing such as tokenization, stop-word handling, stemming, lemmatization, and keyword extraction. | Should Have | US04 | Vaishali | Completed
3 | 3 | US06 | As a user, I want a FastAPI backend endpoint to accept bug files/text and return analysis-ready structured data. | Must Have | US01-US05 | Vaishali | Completed
3 | 3 | US07 | As a developer, I want API documentation through Swagger so that endpoints can be tested easily. | Should Have | US06 | Vaishali | Completed
4 | 4 | US08 | As a developer, I want the preprocessing module tested with sample bug reports to validate extracted fields and error handling. | Must Have | US01-US07 | Vaishali | Completed
4 | 4 | US09 | As a team member, I want my individual module documented and prepared for integration with the multi-agent bug diagnosis platform. | Must Have | US08 | Vaishali | Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US01 | T01 | Study bug-report structure and define preprocessing fields | 2026-07-13 | 2026-07-15 | Vaishali | Development | Completed | 4
US01 | T02 | Implement raw bug-report text preprocessing in Python | 2026-07-14 | 2026-07-17 | Vaishali | Development | Completed | 8
US02 | T03 | Extract exception, priority, file, line number, keywords and stack trace | 2026-07-17 | 2026-07-21 | Vaishali | Development | Completed | 10
US03 | T04 | Generate and save structured JSON output for processed bugs | 2026-07-21 | 2026-07-23 | Vaishali | Development | Completed | 5
US04 | T05 | Implement PDF/TXT upload and text extraction prototype | 2026-07-27 | 2026-07-31 | Vaishali | Development | Completed | 8
US05 | T06 | Implement and test NLP preprocessing operations | 2026-07-31 | 2026-08-04 | Vaishali | Development | Completed | 8
US04 | T07 | Build document summarizer prototype and validate extracted text | 2026-08-04 | 2026-08-07 | Vaishali | Prototype | Completed | 6
US06 | T08 | Set up FastAPI backend and project environment | 2026-08-10 | 2026-08-12 | Vaishali | Development | Completed | 6
US06 | T09 | Implement bug file/text analysis API endpoints | 2026-08-12 | 2026-08-16 | Vaishali | Development | Completed | 10
US07 | T10 | Run backend with Uvicorn and verify Swagger API documentation | 2026-08-16 | 2026-08-18 | Vaishali | Testing | Completed | 4
US08 | T11 | Test preprocessing and API flow with sample bug reports | 2026-08-24 | 2026-08-28 | Vaishali | Testing | Completed | 8
US08 | T12 | Fix environment/path/dependency issues and validate outputs | 2026-08-28 | 2026-09-01 | Vaishali | Debugging | Completed | 8
US09 | T13 | Prepare individual module documentation and integration notes | 2026-09-01 | 2026-09-05 | Vaishali | Documentation | Completed | 6
US09 | T14 | Final review of individual contribution and submission artifacts | 2026-09-05 | 2026-09-06 | Vaishali | Documentation | Completed | 4

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | Day 1 | Need to identify consistent fields from unstructured bug reports. | Defined title, exception, priority, file, line, keywords and stack trace as core fields.
1 | Day 7 | Parsing patterns vary across different bug reports. | Used flexible text/regex-based extraction and tested with sample reports.
2 | Day 1 | PDF/TXT inputs require reliable text extraction before NLP. | Added document text extraction and validated the extracted content.
2 | Day 7 | NLP outputs needed to remain useful for bug analysis. | Tested tokenization, stop-word handling, stemming, lemmatization and keyword extraction.
3 | Day 1 | Backend environment and dependencies had to be configured. | Created/activated virtual environment and installed required packages.
3 | Day 7 | API execution/path issues while running the backend. | Corrected paths and verified FastAPI endpoints using Swagger.
4 | Day 1 | Need to validate preprocessing output before integration. | Tested sample bug reports and checked structured JSON fields.
4 | Day 7 | Individual module needed clear handoff documentation. | Prepared module summary, test evidence and integration notes.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-07-13 | 2026-07-26 | Vaishali | Use structured extraction rules and test with multiple bug samples. | Relying on manually reading raw bug reports. | Keep preprocessing outputs simple and machine-readable. | Completed Python preprocessing and JSON output.
2 | 2 | 2026-07-27 | 2026-08-09 | Vaishali | Validate extracted document text before applying NLP. | Mixing prototype features with final backend requirements. | Continue small, testable NLP tasks. | Completed document/NLP prototype tasks and documented learning.
3 | 3 | 2026-08-10 | 2026-08-23 | Vaishali | Use API-first testing through Swagger while developing. | Using prototype-only framework choices for the final backend. | Continue FastAPI-based modular development. | FastAPI backend and analysis endpoints were validated.
4 | 4 | 2026-08-24 | 2026-09-06 | Vaishali | Run end-to-end checks and maintain submission-ready documentation. | Leaving environment and dependency checks until the end. | Continue testing with representative bug samples. | Validated individual module and prepared integration/submission artifacts.
5
6
7